## Sheet1
Detailed timing
items	due date	days	notes
sequence diagram	01/05/22	2
web app dev	19/05/2022	19
- database creation	02/05/22	1
- classes creation	04/05/22	2
- authentication	07/05/22	3
- getting nearby info	10/05/22	3
- getting services from map	11/05/22	1
- save favourites	16/05/2022	1
- account management
- admin page
- add review
- personnal service page
- map integration as services' page	20/05/22	3
report making	21/05/22	1
presentation	22/05/22	1

maps: