## Sheet1
Detailed timing
items	due date	days	notes
sequence diagram	01/05/22	2
web app dev	19/05/2022	19
- database creation	02/05/22	1
- classes creation	04/05/22	2
- authentication	07/05/22	3	register and login
- getting nearby info	10/05/22	3
- getting services by city and/or type	11/05/22	1	timeframe is low because it’s almost copy paste
- save favourites	12/05/22	1
- create plans	15/05/22	3
- account management	16/05/22	1
- admin account management	17/05/22	1
- optional: map integration as main page	20/05/22	3
report making	21/05/22	1
presentation	22/05/22	1

maps: